## Pan India Summary
PAN INDIA HOTEL PROJECT SUMMARY(AS OF JUNE 2025)
Sl no | Cluster head | Locations covered | Hotels | Total Keys
1 | Renovation | Shack Project | 1 | 20
2 | North Projects | Tapasya-Gurugram, Baddi - Himachal Pradesh, Lucknow, Mussorie, Mall Road Mussorrie,Ambala. | 6 | 512
3 | Mr.Ajith kumar | Pushkar,Bhopal,Chittogarh-Bari sadri,Kattu shamji . | 5 | 423
4 | Mr.Kunal Banerjee | Bhadohi, Jamshedpur, Tezpur, Patna, Bhopal Airport. | 4 | 204
5 | Mr.Vikas Passi | Rajkot,,Nanded,,Gir,Mulshi,Bhuj,Anjar,Bhavnagar,Uruli Kanchan,Mundra ,Vododara. | 13 | 809
6 | Mr.Shiwam Verma | Goa - Dodamarg,Fenicia. | 2 | 257
7 | Mr.Sarvanan | Tirupathi,Vijayawada. | 2 | 91
|  | Total | 32 | 2296

## 1. Additional
Renovation Projects
S.NO. | LOCATION | STATE | HOTEL | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECTS | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK | PROJECT STATUS | ENGINEER / PROJECT MANAGER AT SITE | E/P CONTACT DETAILS
1 | Shack Project | Goa | Royal Orchid Beach Resort & spa |  |  | 20 | [8 empty] | https://workdrive.zohopublic.in/file/9n8pmf28a539d433c4e78806ff66f7cf4706b
1 |  |  |  |  | TOTAL KEYS | 20

## 2. North projects
North Projects
Sl.No | LOCATION | STATE | HOTEL NAME | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECTS | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK as on 28th August | PROJECT STATUS | ENGINEERS/ PROJECT MANAGERS AT SITE | CONTACT DETAILS | Column1
1 | Gurugram | Haryana | Tapasya | Mr. Vijay kapoor | 9910038697 | 128 | 2026-05-01 | Ms.Saylee-total integrated design pvt ltd | https://workdrive.zohopublic.in/file/qusyg9ef214c951f74462b90710cc7fdf1fd4 | 9871237816 | https://workdrive.zohopublic.in/folder/qusyg8c0001c0a6124df3a3dafa2ae787d660 |  |  | https://workdrive.zohopublic.in/file/d7kd5890e5288744446acab55126846884182 | https://workdrive.zohopublic.in/file/idymt1a28e8c06a4d41d78c7bd0808710185f | All the approvals have been issued to project for execution. The projects are happening in full swing . As per the latest discussion with Mr. Kapur , Guest rooms / Trasition Lobby / Reception/ Bar works are in advance stage . ADD/ Banquate halls ceiling height reduction and civil work are started . | Civil &Interior Work in progress | Mr.Anil Chauhan | 9717127878
2 | Ambala | Haryana | Regenta Z | Mr.pavan Agarwal | 9215228328 | 36 | 2026-01-01 | Ms.Suganda chopra |  | 9816800688 |  | https://workdrive.zohopublic.in/folder/116voe17ad800682c47af80f36462640ac03d | https://workdrive.zohopublic.in/file/7l4hk44e98615cccb464eb7e9c4b7633ef2cf | - | https://workdrive.zoho.in/folder/9n8pma0ecd665d05e45c9b0b9b2e784295669 | One mockup work in Progress.
3 | Mall road Mussoorie | Uttarakhand | Regenta Place | Mr. Ashwin | 9105610497 | 45 | 2026-03-25 | Studio line craft - Mr.Vikram Khatri | https://studiolinecraft.in/ | 9811766887 | https://workdrive.zoho.in/folder/9n41ya9a0447883a94f799851a3abfd41ed6d | https://workdrive.zohopublic.in/folder/qusyg90d67765b7934d95bf5f194b12ab2c27 | https://workdrive.zohopublic.in/file/095bx6ed1b4f996dd4342a1bb2598623f41c8 | - | https://workdrive.zohopublic.in/folder/qusyg3bc30b376cfe427881ce0d81fe78fdc6 | All the approvals for mockup room have been shared mockup work in progress. Electrical /HVAC approvals have been issues for working . | Mockup room in progress
4 | Lucknow | Uttar pradesh | Regenta | Mr. Sandeep | 9899522393 | 190 | 2026-12-01 | Design BNK-Mr.Behzad | https://workdrive.zohopublic.in/file/qusygce62f3453d0946039297c7fa063e8acd | 99201 16767 | https://workdrive.zohopublic.in/folder/qusyg32a71378106b4a41a14b57cf99ed3196 | https://workdrive.zohopublic.in/folder/qusygaf6b1398826846edb7550058bd3ac066 | https://workdrive.zohopublic.in/file/qusyg3b6b95f3c43a457b996417237d7bd596 | - | https://workdrive.zohopublic.in/folder/qusyg842a273b31624ebbb65184aabdc519f3 | Rendering of guest room and public area is finalized ,MUR/MEP in progress, | Guest &Corridor design Approved rest in progress
5 | Mussoorie | Uttarakhand | Regenta | Mr. Rishi - CEO | 9899750505 | 70 | 2026-10-01 | Studio whizztech - Tarun kumar | https://workdrive.zohopublic.in/file/qusyge34d476afc4d412782395166c4f7fc44 | 9868087509 | https://workdrive.zohopublic.in/folder/qusygce323cf0f36940cda2302f144c9c59f4 | https://workdrive.zohopublic.in/folder/qusyg006f00a722a646e68d36d6e52b611cb9 | https://workdrive.zohopublic.in/file/d7kd5cd7a5fb817b64a9bbcbb9bade4683f75 | - | https://workdrive.zohopublic.in/folder/qusyga4657f27954d4479a98629f0c37268b4 | Site visit is completed Inputs have been shared for detail Drawings and Renderings. The actual measurements yet to receive from site. Dicussed with Mr. Rishi and they could not able to proceed as severe rain fall is happening. | It is in design stage
6 | Baddi | Himachal Pradesh | Regenta Place | Mr.Shravan | 92186 72900 | 43 | TBD | [5 empty] | https://workdrive.zoho.in/folder/9n8pmf5b4ba03170e4d1ab1a1fe5766fb004b |  | https://workdrive.zoho.in/folder/9n8pmf24d6669c73a48648b214c1c57fd6380 | review to be done
7 | Darbar Hall
6 |  |  |  |  | Total | 512

## 3. Mr.Ajith Kumar
CLUSTER HEAD - MR. AJITH KUMAR
S.NO. | LOCATION | STATE | HOTEL NAME | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECTS | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK | PROJECT STATUS | ENGINEERS / PROJECT MANAGERS AT SITE | E/P CONTACT DETAILS
1 | Kattu shamji | Rajasthan | Regenta | Mr. Himanshu | 9352945772 | 120 | 2025-10-04 | ARCH POINT -Vasuda goyal | https://www.archpoint.in/ | 7691099000 | https://workdrive.zohopublic.in/folder/qusygd6b8b63993df454abebbafbf73b2ca9a | https://workdrive.zohopublic.in/folder/qusyge274ad472c4249f4ab9e7496514cec2e | https://workdrive.zohopublic.in/file/qusyg16dfd9ad70224d3a9e8fa5655deb6f93 | https://workdrive.zohopublic.in/file/d7kd58d9a4c56144243e0b56afc0e70584e32 | https://workdrive.zoho.in/folder/9n8pmd5d04502ccdd4bf1aa2ffe9cc5634b8c | Work in progress ,all the approval have been given. Handover in progress.. | Civil and interior work in progress
2 | Bhopal | Madya pradesh | Regenta kailash | Mr. Yogendra tripathi | 9425511557 | 72 | 2025-12-04 | SATYENDRA - DESIGN NAVIGATE | https://workdrive.zohopublic.in/folder/qusygd280634fb2574f6bb6f6041a766c9da6 | 9717980305 |  | https://workdrive.zohopublic.in/folder/qusyg1a86a8adb6164873a4b8bf4852a6524d | https://workdrive.zohopublic.in/file/qusyg3ce6f9245cd641db96f678ed12da8dbf | https://workdrive.zohopublic.in/file/d7kd596196f32b5f94d1ca0504cac07bf45c3 |  | Work is under hold ,no project work is happening the project shall be completed by end of dec. | Interior and MEP work in progress
3 | Pushkar | Rajasthan | Regenta resort | Mr. Dinesh yadav | 9828033340 | 104 | 2025-11-25 | Design Frame | https://www.facebook.com/designframe30/ | 9352588132 | https://workdrive.zohopublic.in/file/gaqr18972050a3522423c9e30a5c1499f16a8 |  |  | https://workdrive.zohopublic.in/file/d7kd5e12435e83e21427c92ff2b3a17349c34 | https://workdrive.zoho.in/folder/9n8pm551ce5d20c144c209165f04bed601bba | meeting to be scheduled on 2nd week of october | Civil and interior work in progress
4 | Chittogarh, bari sadri | Rajasthan | Regenta resort | Mr. Sanjay chaudhary | 9001853733 | 57 | 2026-01-26 | Bhate ji Bedwas | NA | 9414733276/ 7014521966 |  |  | https://workdrive.zohopublic.in/file/d7kd5e52d5a7f511542fb8815ed9565de699a | - | https://workdrive.zohopublic.in/folder/qusygb44b8ee04d25448c81ed8182b28ddace | No updates from site .Mr ajith is in touch with owners. | Civil and interior work in progress
5 | Bhopal Airport | Madya pradesh | Regenta | Mr.Prateek | 7000823459 | 70 | 2026-11-25 | Ajeet lalwani | https://www.facebook.com/share/16JJXkegQV/?mibextid=wwXIfr | 9425024008 |  |  | https://workdrive.zohopublic.in/file/z2rn5c90849a3526140848dfed3bd8d666fee | - |  | We have asked for the rendering for MUR and Public areas
5 |  |  |  |  | Total | 423

## 4. Mr. Kunal
CLUSTER HEAD - MR. KUNAL BANERJEE
S.NO. | LOCATION | STATE | CLUSTER HEAD | HOTEL | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECTS | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK | PROJECT STATUS | ENGINEER / PROJECT MANAGER AT SITE | CONTACT DETAILS
1 | Tezpur | Assam | Mr Kunal | Regenta Place | Mr Nikhlesh Satani | 9954899644 | 38 | 2026-03-26 | Food service design india | https://workdrive.zohopublic.in/folder/qusyg6065c4e335ba4193b60fabfafb9649fc | 9810086477 | https://workdrive.zohopublic.in/folder/qusyg843f74f0d76248f7833875ba60c672b2 |  |  | https://workdrive.zohopublic.in/file/d7kd5e0c9bea498e94e1d86793becdf5a56f2 | https://workdrive.zoho.in/folder/9n8pm90eceb3c92244272957938deede4c348 | We had a review on 16th august with Mr. Arjun and Mr. Baljee. All approvals have been given and final drawings and renderings are awaited . | Civil & interior work in progress
2 | Bhadohi | Uttar Pradesh | Mr. Kunal | Regenta Central | Mr. Puneet Mehra | 9335789978 | 56 | 2025-10-25 | Narayan jariwala-harmony interior and associates | https://workdrive.zohopublic.in/folder/qusygddb751c59db848a98f94561a2296e9e7 | 9426115187 | https://workdrive.zohopublic.in/folder/qusyg5b50a57d8fa04d649cd6f0a8d899108c | https://workdrive.zohopublic.in/folder/qusygea2c3b01ff314791b7df664ad9a8c609 |  | https://workdrive.zohopublic.in/file/d7kd58244f99f687341d9bef7dd5662380829 | https://drive.google.com/drive/folders/1N3046mw_kKSkA8__ZSuvY77WoxuoW76h?usp=drive_link | Work Progress is very slow and owner wanted to open the property by October -25 which is nonrealistic based on the progress. We have asked for Gantt chart a month back to know the completion and we are yet to receive the details from the owners. | Civil and Interior work in progress | Mr. Deepak Tiwari | 8573037407
3 | Patna | Bihar | Mr.Kunal | Regenta Z | Mr.Anurag | 9934280454 | 50 | 2025-11-25 | Japcon Architects | https://workdrive.zoho.in/folder/eul5o72bc88ef922e4bdeb03ab1a8827cd0f7 | 9886083430 | https://workdrive.zohopublic.in/folder/d7kd5ebbfb63df5f04987a495aa76b9a89c39 |  | https://workdrive.zohopublic.in/file/n8aq8bad2560118ed43d2801661dafc34c449 | https://workdrive.zohopublic.in/file/d7kd5a7e3924bb773404d8757cb910112ab01 |  | The design we have approved and shared . Work progress is very slow. | Designer to be Appointed
4 | Jamshedpur | Jharkhand | Mr Kunal | Regenta central | Mr. Harish | 9234000011 | 60 | 2026-08-25 | Dimensions graph | https://dimensiongraph.com/ | 9163755866 | https://workdrive.zohopublic.in/folder/qusyge6e299ce229c4147a34407132e99e9eb | https://workdrive.zohopublic.in/folder/d7kd5ecb4fdc5239f42c8964eae2eecce3ebe |  | - | https://workdrive.zoho.in/folder/9n8pmc828b7dd1e80474faaea67151e9792e6 | The mockup room has been approved and it is in progress | Mockup room in progress
4 | [5 empty] | Total | 204

## 5. Mr. Vikas passi
CLUSTER HEAD - MR. VIKAS PASSI
0 | LOCATION | STATE | HOTEL | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECTS | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK | PROJECT STATUS | ENGINEERS / PROJECT MANAGERS AT SITE | CONTACT DETAILS2
1 | RAJKOT | GUJARAT | Regenta Central | Mr. Bakir Gandhi | 9374021500 | 70 | 2025-12-01 | Mr. MEHBOOB LIGHTWALA |  | 9824009327 | https://workdrive.zohopublic.in/folder/qusygc0a5bcabeab74f038154b1f66ca51c44 |  |  | https://workdrive.zohopublic.in/file/lmporc2be66ce1ba64904870d925c8e7c8bb4 | https://workdrive.zoho.in/file/9n8pme7d889243a88419784a608e0bdc8a8e8 | Work progress is very slow. Mr. Rakesh had a meeting with Mr.Bakir Gandhi about the ADD/ BOH to complete . | Civil and Interior Work in progress | Mr.Pravin parmar | 9904260771
2 | Rajkot - Greenland Chokdi | Gujarat | Regenta place | Mr.Lalit Savaliya | 9825192234 | 50 | 2025-12-25 | Mr.Vipul Godaliya |  | 8460807854 |  |  | https://workdrive.zohopublic.in/file/gzano4ff33ea382e54f0a8d8bcfdb488ec5f1 |  |  | The Kick off meeting we had on 28tgh August and the rooms are in progress. We need to give inputs of banquet halls and terrace.
3 | NANDED | MAHARASHTRA | Regenta Central | Mr. Ashish Kotgire | 9422170979 | 60 | 2025-12-01 | Mr. Rahul Malviya |  | 9920840633 | https://workdrive.zohopublic.in/folder/qusyg6bc881e93bf64c47b9bfa41fda55c47d | https://workdrive.zohopublic.in/folder/qusygb2b0a2d4fb4f4da2a4e6430445f63239 |  | https://workdrive.zohopublic.in/file/d7kd502e422bf19554027b14a6bf45bc43039 | https://workdrive.zoho.in/folder/9n8pm1b22dd19b6104c75b83c7b6e42294180 | Work is in Progress in slow pace. | Civil and Interior Work in progress | Mr.Aditya Kotgire | 9403590979
4 | Bhuj | GUJARAT | Regenta central Bhuj | Mr.Kiren Chedda | 9726997880 | 59 | 2025-10-25 | Mr. Anil Thakkur | https://workdrive.zohopublic.in/folder/qusyg5f6e932660a2402ab330ab7f418a40cd | 9870060053 | https://workdrive.zohopublic.in/folder/qusyg8878189c4ba24491a7b0edba63962f64 | https://workdrive.zohopublic.in/folder/qusyg675100a82a8e4df3b4b9519ee7ad6d9c | https://workdrive.zohopublic.in/file/qusyg642a72db472d4e8698e28b1905b3feb9 | https://workdrive.zohopublic.in/file/d7kd575e05f4d3dca40c5a216f63d860db437 | https://workdrive.zoho.in/folder/9n8pm01ddfc7ebac44d38bc87efaef8219416 | Work is in Progress .Snagging and pending work Fallow up is going on by Pre opening Team | Civil and Interior Work in progress | Mr. Dhaval | 9820263940
5 | Anjar | GUJARAT | Regenta INN ANJAR | Mr. Harish Chauhan | 9879198077 | 44 | 2025-10-25 | Mr. Nirav Sonagra | https://workdrive.zohopublic.in/folder/qusyge94dbb6e64a34b85be254ea01f70542b | 9824113661 | https://workdrive.zohopublic.in/folder/qusyg8c1254f35f0241c986c47babbef34777 | https://workdrive.zohopublic.in/folder/qusyga03a7bf3afbe4728b6742401f18f1e45 |  | https://workdrive.zohopublic.in/file/d7kd5f4382a73e7f445ff9d3f4c39b92ec0e1 | https://workdrive.zoho.in/folder/9n8pm85d64cd7d14c4f7780753d9a6f27b248 | Work is slow | Structural work is completed ,civil and interior works are pending | Mr .Haresh Chauhan Mr.Ramesh Solanki | 9879198077 9638296947
6 | Bhavnagar | GUJARAT | Regenta Resorts | Mr. Yashraj Kamdar | 91 73741 111 | 65 | 2025-12-25 | Mr.Narendra Singh Gohil | https://nandinfrastructure.com/team/narendrasinh-jilubha-gohil/ | 9824245252 | https://workdrive.zohopublic.in/folder/qusyg25cecd5e3d374bbfa34ca2ac31256c72 | https://workdrive.zohopublic.in/folder/qusyg45cc9c0a7f1a4996861412a871761af2 | https://workdrive.zohopublic.in/file/qusygeac3729e37d642a481438a49935be854 | https://workdrive.zohopublic.in/file/d7kd53d6cbc548aae4111b0eaf016cef19a9a | https://workdrive.zoho.in/folder/qusyg900b96820f8541f7a88858f84327bc25 | Review is happening in the month of October. | Civil and Interior Work in progress | Tina Bhai | 8155057272
7 | Bharti / Uruli kanchan | MAHARASHTRA | Regenta Resort | Mr.Ravindra Balu Bharti | 7570909090 | 70 | HOLD |  |  |  | https://workdrive.zohopublic.in/folder/qusyg24934f08b81849979cb4485b702efcd3 |  | https://workdrive.zohopublic.in/file/gaqr14ca98be02fab4810aa2b354f45ff7411 | - |  | 20 ROOMS ARE OPERATIONAL | work is on hold
8 | Gir | GUJARAT | Regenta Central | Mr. Harish Balani | 61410073369 | 80 | 2026-03-26 | Mr. Rishi |  | 9723143430 |  | https://workdrive.zohopublic.in/folder/qusygf48229e2cee344e9880ca1fcd129e8ee | https://workdrive.zohopublic.in/file/qusyg939e03238ba14a8197ae55a120e33105 | https://workdrive.zohopublic.in/file/9n8pm26fa6e61fcd84a1190044c368529ce3f | https://workdrive.zoho.in/file/9n8pme139f7a209174f99be937f7b9efeadab | Work is very slow .Detailed meeting to be doJ10:Q10ne. Owner in austrila and we are arranging review meeting by 10th of October | Civil and Interior Work in progress | Mr.pravin parmar Mr.Hasu | 9904260771 9099283282
9 | Mulshi | MAHARASHTRA | Regenta Central | Mr. Harish | 9822023135 | 65 | 2026-03-26 | Ms. Poorva Shinde | https://workdrive.zohopublic.in/folder/qusyge94dbb6e64a34b85be254ea01f70542b | 9011074334 | https://workdrive.zohopublic.in/folder/qusyg4bf61df199ba4b9b969bebf50cf38fa1 | https://workdrive.zohopublic.in/folder/qusygc0422d7e80ec4af5888efcf20dcda36e | https://workdrive.zohopublic.in/file/qusyg4a5b0afc191a4e4fa2e4a86b437c4c1d | - | https://workdrive.zoho.in/folder/9n8pmbaf179fad16b4269ab61f387e5d043be | All the approvals have been given from project side .Progress Review is pending. | Civil ,Interior & MEP Works in progress | Mr.Yogesh Khaliakar Mr.Sunil | 9922448303 9923023200
10 | Panchgani | MAHARASHTRA | Regenta Resort | Mr. Gaikwad | 9820803060 | 60 | HOLD | [6 empty] | - | - |  | Stopped due to some Environmental issues
11 | Mundra | Gujarat | Regenta | Mr.Kishan | 7283851909 | 101 | TBD | [5 empty] | https://workdrive.zohopublic.in/file/gaqr1243e6dc63f164ecfa9ad8f2e728ce767 | - | - | We had initial meeting . Basic preperation is happening at site . | Designing stage
12 | Vododara | Gujarat | Regenta Z | Mr.Naresh | 9898796888 | 37 | 2025-11-25 | Mr.Prashanth | https://workdrive.zohopublic.in/file/idymte91df033385e453b815cc25785446c7b | 9501440007 | https://workdrive.zohopublic.in/folder/qusyga4853687d90d474abf86fb9a462d5cae | https://workdrive.zohopublic.in/folder/qusyg680d185fd3d340fc8cfb74bfd64f18e0 |  | - | https://workdrive.zohopublic.in/folder/zz7163ec09da5685d4f0e96abf4a2fcd92198 | Site Visit is done and all inputs as per Regenta Z are given. Work in Full swing and they wanted to open the hotel by end of september. | Civil & interior Work In progress
13 | Ahmedabad | Gujarat | Regenta place | Mr.Romil patni | 9586099888 | 48 | 2025-10-25 | [5 empty] | https://workdrive.zohopublic.in/file/idymt3de683894e2d47acb86ad78dee9e0c81 |  |  | Site Visit is done and all inputs as per Regenta Z are given. Work in Full swing and they wanted to open the hotel by end of september.
13 |  |  |  |  | TOTAL | 809

## 6. Mr. Shivam verma
CLUSTER HEAD - MR. SHIWAM VERMA
S.NO. | LOCATION | STATE | HOTEL | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECTS | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK | PROJECT STATUS | ENGINEER / PROJECT MANAGER AT SITE | E/P CONTACT DETAILS
1 | Dodamarg | Goa | Regenta | Mr. Bharat | 8800590867 | 219 | 2026-03-01 | Mr poorva shinde | https://workdrive.zohopublic.in/folder/qusyge94dbb6e64a34b85be254ea01f70542b | 9011074334 | https://workdrive.zohopublic.in/folder/qusyg925f04aaf23244dbaea58d4de460ed34 | https://workdrive.zohopublic.in/folder/qusyg203a4fbf3a73483585f5cf5f9a94ed10 |  | https://workdrive.zohopublic.in/file/9n8pme1d7190aa2eb4e958e48cb6f1de0db01 | https://workdrive.zohopublic.in/folder/qusyg40f9e4c94d5c49939c9c1f652529d9b5 | As per the latest meeting we had works are happening as per the ROHL approval done.
2 | Fenicia | Goa | Crestoria | Mr. |  | 38 | 2025-12-01 | [7 empty] | https://feniciaresort.com/ | we had detailed review in the meeting held on 29 sept.
2 |  |  |  |  | TOTAL KEYS | 257

## 7. Mr. Sarvanan
CLUSTER HEAD - MR . SARVANAN
S.NO. | LOCATION | STATE | HOTEL | OWNER | CONTACT DETAILS | NO. OF KEYS | OPENING DATE | ARCHITECT | ARCHITECT PORTFOLIO | CONTACT DETAILS OF ARCHITECT | ARCHITECTURAL DRAWINGS | RENDERINGS | INTERNAL MEMORANDUM | PROJECT SCHEDULE | PRESENT WORK STATUS AT SITE | PROJECT FEEDBACK | PROJECT STATUS | ENGINEER / PROJECT MANAGER AT SITE | CONTACT DETAILS2
1 | Thirupathi | ANDHRA PRADESH | Regenta central | Mr. Girish | 9004570963 | 54 | 2025-12-01 | Mr. Harain Murthy | https://workdrive.zohopublic.in/file/qusygef1af613a2e24b3caa9b463608386761 | 9590194154 | https://workdrive.zohopublic.in/folder/qusyge9fca32670204053b0cacb3142045e1b | https://workdrive.zohopublic.in/folder/qusygb9d0610e40194ab19206964358aa0eac |  | - | https://workdrive.zohopublic.in/folder/9n8pm75a3fb3aead6409890de1a9e584a4eb3 | work is happening in full swing.Property will be ready by end of december
2 | Vijaywada | ANDHRA PRADESH | Regenta Z | Mr.Mohan |  | 37 | 2025-12-25 | Ms.Divya sharma verneker | https://www.idadubai.com/ | 9741785607 |  |  |  | - | https://workdrive.zohopublic.in/folder/d7kd5713c23bfdb3e459da9af1ee1be994380 | survey is completed. Inputs have been given as per brand specific. We have asked them to complete one mock up asap.
2 |  |  |  |  | TOTAL KEYS | 91